## Instructions
State Advocacy Day Project Plan Instructions
Background
This document is designed to help state chapters plan for their state advocacy days.
There are four tabs (found at the bottom of the document):
- Instructions Tab - how to use this document and important information to know when working with Microsoft Excel.
- Task List Tab - designed to be all-inclusive of action items needed for a successful advocacy day. See an expanded description below.
- Legislative Appointments Tab - allows you to track appointments in the same location as the project plan.
- Do Not Delete Tab - holds valuable formulas and conditional formatting for the 'Task List' tab. This tab has been locked and hidden from view.
The Project Plan
There are four phases to this project plan:
Conception - otherwise known as the 'kick-off' phase, this includes establishing a budget for the day, working with Chapter leadership and the ACS State Affairs team to identify the Chapters policy priorities, booking venues, and creating a registation process.
Launch - 24 hours prior to the state advocacy day and finishes at the closing of the day.
Evaluation - just as important as the three other phases, this allows us to close the feedback loop on the state advocacy day and maintain momentum as a result.
Managing the Task List Tab
Each task is assigned to a project phase and then prioritized based on which task needs to be completed first.
The Task List tab has been built so that you can enter the date of your state advocacy day in the top gray cell on line 2 of the document. Once you have entered the the date of your state advocacy day, the due dates for each task item will auto populate in column F based on how many days out from the state advocacy day (column E) the task needs to be completed.
The Project Start Date in the gray cell on line 3 on the Task List tab will automatically populate to 120 days prior to your state advocacy day.
The Phase, Category, Status, and Risk Level columns (A, B, J, and K respectively) have drop-down menus in each cell. If you click on the cell, a small arrow will appear to the right of the cell. Click on the arrows to access the drop down menu.
The Task column (column D) included every task that needs to be completed during the planning process. This is an imperfect list and you will more than likely need to add / edit your own tasks as you continue in the process.
The Days Until Advocacy Day column (column E) is how many days until the state advocacy day the task item needs to be completed. You can adjust these numbers according to your needs.
The Due Date column (column F) is calculated based on the Days Until Advocacy Day column (column E).
The Assigned Lead column (column G) is for assigning a person to a specific task. While Chapter Executive Directors are responsible for the entire day, it may be helpful to delegate certain tasks to other Chapter leadership.
The Start and End Date columns (columns F and G, respectively) will need to be filled out once you know the date of your state advocacy day. Note that multiple tasks can be completed in one day.
The Risk Level column (column I) is to highlight if a certain task needs more attention than others due to hurdles that may be in the way.
The Risk Mitigator column (column J) is to assign someone to a task if the level of risk increases throughout the planning process. For example, the task item of reaching out to residency program directors to invite residents to the state advocacy day might become a "high" risk if the person emailing them has not recieved a response. For this task, the risk mitigator might be another Chapter member who works with the residency program director in question. The solution may be the Chapter member stopping by the residency program director's office to speak in person.
The Notes column (column K) is good to use for any additional explanations needed for the status of a task.
How to Insert a New Task or Delete a Current One:
While the task list is designed to be comprehensive, you may want to add additional tasks specific to your state advocacy day planning or delete ones that do not apply.
To delete a task item, click on the line number of the row on the left-hand side of the screen. The entire row of cells should be highlighted. Right click on the highlighted row and click, 'Delete' on the drop down menu.
To add to task item, click on the line number of the row on the left-hand side of the screen that you would want to insert the item above. The entire row of cells should be highlighted. Right click on the highlighted row and click, 'Insert' on the drop down menu. Then select 'Entire Row' and press 'OK.' Once you have your new row, you will want to re-order the numbers in column A. Then select what Phase of the project the task item belongs to and then the Category.
Next, add your task item. Underneath the Days Until Advocacy Day column (column E), list how many days out from your state advocacy day you believe the task item should be completed. Then under the Due Date column (column F) select the cell immediately above your new row / task item. Grab the lower right hand corner of the cell and drag down to the new one. This will make sure that your new task item has the appropriate formulas to calculate your due date.

## Task List
| Advocacy Day | 2023-09-30
| Project Start Date | 2023-06-02
# | Phase | Category | Task | Days Until Advocacy Day | Due Date | Assigned Lead | Status | Risk Level | Risk Mitigator | Notes
1 | Conception
1.01 | Conception | Budget | Assess and establish a budget for state advocacy day | 120 | 2023-06-02 |  | Complete | High
1.02 | Conception | Establishing Goals | Schedule a kick-off call with ACS State Affairs Team | 120 | 2023-06-02 |  | Not Started | Low
1.03 | Conception | Establishing Goals | Review current state legislation; Consult ACS State Affairs Team | 120 | 2023-06-02 |  | Not Started | Low
1.04 | Conception | Budget | Apply for the ACS State Advocacy Grant (if needed) | 118 | 2023-06-04 |  | Not Started | Low
1.05 | Conception | Establishing Goals | Consult with the state medical society on their priority policy issues for the year; Consult ACS State Affairs Team | 118 | 2023-06-04 |  | Not Started | Low
1.06 | Conception | Selecting a Date | Review your state's legislative calendar | 117 | 2023-06-05 |  | Not Started | Low
1.07 | Conception | Selecting a Date | Identify any other events that may conflict with potential dates, including other state advocacy days and conferences | 117 | 2023-06-05 |  | Not Started | Low
1.08 | Conception | Establishing Goals | Meet with Chapter leadership and legislative committee (if available) to decide what policy priorities the Chapter will pursue, format, and date | 117 | 2023-06-05 |  | Not Started | Low
1.09 | Conception | Choosing a Format | Decide the format of your state advocacy day | 117 | 2023-06-05 |  | Not Started | Low
1.1 | Conception | Choosing a Meeting Venue | Identify potential meeting venues near your State Capitol | 116 | 2023-06-06 |  | Not Started | Low
1.11 | Conception | Choosing a Meeting Venue | Request quotes for reserving your meeting venue | 115 | 2023-06-07 |  | Not Started | Low
1.12 | Conception | Choosing a Meeting Venue | Tour all potential meeting venues | 110 | 2023-06-12 |  | Not Started | Low
1.13 | Conception | Catering | Decide what level of catering the Chapter will provide | 110 | 2023-06-12 |  | Not Started | Low
1.14 | Conception | Catering | Identify potential catering companies | 109 | 2023-06-13 |  | Not Started | Low
1.15 | Conception | Catering | Request quotes from catering companies | 105 | 2023-06-17 |  | Not Started | Low
1.16 | Conception | Transportation | Identify transportation services to take Chapter members from the meeting venue to the Capitol Building | 104 | 2023-06-18 |  | Not Started | Low
1.17 | Conception | Transportation | Request quotes from transportation services | 104 | 2023-06-18 |  | Not Started | Low
1.18 | Conception | Choosing a Meeting Venue | Reserve your meeting venue | 103 | 2023-06-19 |  | Not Started | Low
1.19 | Conception | Meeting Presentations | Book AV equipment for the meeting | 103 | 2023-06-19 |  | Not Started | Low
1.2 | Conception | Recruiting Participants | Set up a registration form and link for Chapter members | 101 | 2023-06-21 |  | Not Started | Low
1.21 | Conception | Recruiting Participants | Create a landing page on your Chapter website to advertise the registration | 101 | 2023-06-21 |  | Not Started | Low
1.22 | Conception | Recruiting Participants | Reach out to all Chapter leadership, CoC State Chair, and COT State Chair to strongly encourage participation | 101 | 2023-06-21 |  | Not Started | Low
2 | Production
2.01 | Production | Advertising the Day | Send out "Save the Dates" | 100 | 2023-06-22 |  | Not Started | Low
2.02 | Production | Advertising the Day | Post "Save the Date" to social media | 100 | 2023-06-22 |  | Not Started | Low
2.03 | Production | Hotel Accomodations | Reserve a block of rooms for out-of-town attendees; preferrably close to meeting venue | 99 | 2023-06-23 |  | Not Started | Low
2.04 | Production | Hotel Accomodations | Notify ACS State Affairs staff and any guest speakers of hotel block before advertising it to the greater group | 98 | 2023-06-24 |  | Not Started | Low
2.05 | Production | Recruiting Participants | Work with Chapter leadership to identify residency program directors in the state and their contact information | 98 | 2023-06-24 |  | Not Started | Low
2.06 | Production | Recruiting Participants | Reach out to resident program directors and ask if they have a few residents they could allow to participate | 98 | 2023-06-24 |  | Not Started | Low
2.07 | Production | Scheduling Legislative Appointments | Reach out to legislative offices who are sponsoring bills the Chapter is supporting and ask if there are specific legislators the Chapter should target for additional support; Consult ACS State Affairs Staff | 97 | 2023-06-25 |  | Not Started | Low
2.08 | Production | Scheduling Legislative Appointments | Identify state legislators that sit on health committees within the House and Senate | 97 | 2023-06-25 |  | Not Started | Low
2.09 | Production | Scheduling Legislative Appointments | Create your legislator target list; Consult ACS State Affairs Team for contact information | 96 | 2023-06-26 |  | Not Started | Low
2.1 | Production | Scheduling Legislative Appointments | Identify the time block within your state advocacy day format to book legilsative appointments | 95 | 2023-06-27 |  | Not Started | Low
2.12 | Production | Scheduling Legislative Appointments | Email or call legislators to request legislative appointments | 95 | 2023-06-27 |  | Not Started | Low
2.13 | Production | Meeting Presentations | Identify what presentations to have at the meeting | 95 | 2023-06-27 |  | Not Started | Low
2.14 | Production | Meeting Presentations | Identify speakers for the meeting presentations | 95 | 2023-06-27 |  | Not Started | Low
2.15 | Production | Meeting Presentations | Invite speaker #1 to the meeting | 95 | 2023-06-27 |  | Not Started | Low
2.16 | Production | Meeting Presentations | Invite speaker #2 to the meeting | 95 | 2023-06-27 |  | Not Started | Low
2.17 | Production | Meeting Presentations | Invite speaker #3 to the meeting | 95 | 2023-06-27 |  | Not Started | Low
2.18 | Production | Meeting Presentations | Invite speaker #4 to the meeting (if needed) | 95 | 2023-06-27 |  | Not Started | Low
2.19 | Production | Meeting Presentations | Ensure that speakers have hotel and travel booked | 92 | 2023-06-30 |  | Not Started | Low
2.2 | Production | Advertising the Day | Invite members to register and reserve a hotel room | 90 | 2023-07-02 |  | Not Started | Low
2.21 | Production | Advertising the Day | Post registration info on social media | 90 | 2023-07-02 |  | Not Started | Low
2.22 | Production | Building a Briefing Packet | Order two sets of folders in two different colors for briefing packets - bonus points if folders can have ACS Chapter branding (similar to ACS Leadership and Advocacy Summit) | 90 | 2023-07-02 |  | Not Started | Low
2.23 | Production | Building a Briefing Packet | Create fact sheet for priority issue #1; View toolkit for template; Print one for each folder | 85 | 2023-07-07 |  | Not Started | Low
2.24 | Production | Building a Briefing Packet | Create fact sheet for priority issue #2; View toolkit for template; Print one for each folder | 80 | 2023-07-12 |  | Not Started | Low
2.25 | Production | Building a Briefing Packet | Create fact sheet for priority issue #3; View toolkit for template; Print one for each folder | 75 | 2023-07-17 |  | Not Started | Low
2.26 | Production | Building a Briefing Packet | Create fact sheet for priority issue #4; View toolkit for template; Print one for each folder | 70 | 2023-07-22 |  | Not Started | Low
2.27 | Production | Advertising the Day | Send out reminder email to encourage members to register | 70 | 2023-07-22 |  | Not Started | Low
2.28 | Production | Advertising the Day | 1st reminder on social media | 70 | 2023-07-22 |  | Not Started | Low
2.29 | Production | Building a Briefing Packet | Create a list of Chapter leadership and staff with their contact information (Be sure to include Chapter branding on the list); Print one for each folder | 65 | 2023-07-27 |  | Not Started | Low
2.3 | Production | Building a Briefing Packet | Find a map of the capitol building; Print one for each Chapter member folder | 65 | 2023-07-27 |  | Not Started | Low
2.31 | Production | Building a Briefing Packet | Create a state advocacy day evaluation form; View toolkit for tempalte; Print one for each Chapter member folder | 65 | 2023-07-27 |  | Not Started | Low
2.32 | Production | Building a Briefing Packet | Create a legislative appointment report worksheet; View toolkit for tempalte; Print 3 to 4 copies for each Chapter member folder | 65 | 2023-07-27 |  | Not Started | Low
2.33 | Production | Building a Briefing Packet | Include two sheets of blank paper with Chapter logo in each Chapter member folder (for members to take notes) | 65 | 2023-07-27 |  | Not Started | Low
2.34 | Production | Building a Briefing Packet | Print ACS Fact Sheet: "How to Master the Legislative Appointment" for each Chapter member folder | 65 | 2023-07-27 |  | Not Started | Low
2.35 | Production | Building a Briefing Packet | Create the State Advocacy Day schedule; View toolkit for template; Print one for each Chapter member folder | 60 | 2023-08-01 |  | Not Started | Low
2.36 | Production | Transportation | Book transportation services | 50 | 2023-08-11 |  | Not Started | Low
2.37 | Production | Catering | Arrange for pick-up and drop off of catering (if needed) | 40 | 2023-08-21 |  | Not Started | Low
2.38 | Production | Evaluation Forms | Create a method of collection for all evaluation forms at the end of the State Advocacy Day | 40 | 2023-08-21 |  | Not Started | Low
2.39 | Production | Meeting Materials | Order lanyards for name tags (if needed) | 40 | 2023-08-21 |  | Not Started | Low
2.4 | Production | Meeting Materials | Order name tags for meeting; Note - order clip ons and not sticky tags | 40 | 2023-08-21 |  | Not Started | Low
2.41 | Production | Meeting Materials | Order pens for Chapter members to use during meeting | 40 | 2023-08-21 |  | Not Started | Low
2.42 | Production | Meeting Materials | Design sign for meeting venue | 35 | 2023-08-26 |  | Not Started | Low
2.43 | Production | Meeting Materials | Order sign for meeting venue | 35 | 2023-08-26 |  | Not Started | Low
2.44 | Production | Meeting Materials | Order display easel | 35 | 2023-08-26 |  | Not Started | Low
2.45 | Production | Advertising the Day | Send out second reminder email | 30 | 2023-08-31 |  | Not Started | Low
2.46 | Production | Advertising the Day | 2nd reminder on social media | 30 | 2023-08-31 |  | Not Started | Low
2.47 | Production | Meeting Materials | Print information on how to update voter registration and put on display during meeting | 20 | 2023-09-10 |  | Not Started | Low
2.48 | Production | Building a Briefing Packet | Include copies of public statements, action alerts, or letters of testimony submitted by the Chapter; Print one for each folder | 20 | 2023-09-10 |  | Not Started | Low
2.49 | Production | Catering | Confirm catering order | 20 | 2023-09-10 |  | Not Started | Low
2.5 | Production | Choosing a Meeting Venue | Confirm meeting venue | 15 | 2023-09-15 |  | Not Started | Low
2.51 | Production | Transportation | Confirm transportation reservation | 15 | 2023-09-15 |  | Not Started | Low
2.52 | Production | Advertising the Day | Send out third reminder email | 10 | 2023-09-20 |  | Not Started | Low
2.53 | Production | Advertising the Day | 3rd reminder on social media | 10 | 2023-09-20 |  | Not Started | Low
2.54 | Production | Scheduling Legislative Appointments | Confirm all legislative appointments | 10 | 2023-09-20 |  | Not Started | Low
2.55 | Production | Building a Briefing Packet | Order all printing for briefing folders | 10 | 2023-09-20 |  | Not Started | Low
2.56 | Production | Meeting Presentations | Collect all slide decks and materials from meeting speakers | 10 | 2023-09-20 |  | Not Started | Low
2.57 | Production | Meeting Materials | Print out registration list to check in Chapter members | 5 | 2023-09-25 |  | Not Started | Low
2.58 | Production | Meeting Materials | Print name tags for Chapter members attending | 5 | 2023-09-25 |  | Not Started | Low
2.59 | Production | Building a Briefing Packet | Create appointment schedule with room locations and contact information of staffers Chapter members are meeting with; Print one for each Chapter member folder | 5 | 2023-09-25 |  | Not Started | Low
2.6 | Production | Meeting Presentations | Send email to all speakers with briefing folder materials and any last minute details | 5 | 2023-09-25 |  | Not Started | Low
2.61 | Production | Building a Briefing Packet | Stuff briefing folders | 5 | 2023-09-25 |  | Not Started | Low
2.62 | Production | Advertising the Day | Social media post to say "Can't wait to see you there" | 1 | 2023-09-29 |  | Not Started | Low
3 | Launch
3.01 | Launch | Meeting Materials | Email a tentative schedule for each attendee including legislative appointments | 1 | 2023-09-29 |  | Not Started | Low
3.02 | Launch | Other | Check the weather and include in courtesy email for Chapter members | 1 | 2023-09-29 |  | Not Started | Low
3.03 | Launch | Advertising the Day | Send an email to those participating providing any last-minute updates, reminders, and digital copies of briefing materials | 1 | 2023-09-29 |  | Not Started | Low
3.04 | Launch | Advertising the Day | Post to social media the day of the state advocacy day to stir up interest | 0 | 2023-09-30 |  | Not Started | Low
3.05 | Launch | Catering | Pick up or drop off catering (if needed) | 0 | 2023-09-30 |  | Not Started | Low
3.06 | Launch | Meeting Materials | Set up registration table and pass out meeting materials | 0 | 2023-09-30 |  | Not Started | Low
3.07 | Launch | Meeting Presentations | Set up laptop with meeting presentations and ensure all av is working | 0 | 2023-09-30 |  | Not Started | Low
4 | Evaluation
4.01 | Evaluation | Follow-up Items | Collect all photos taken throughout the day from Chapter members | 0 | 2023-09-30 |  | Not Started | Low
4.02 | Evaluation | Advertising the Day | Post summary / photos of the advocacy day to social media outlets | 0 | 2023-09-30 |  | Not Started | Low
4.03 | Evaluation | Thank You Emails | Send thank you emails on behalf of the Chapter leadership to every legislative office that had appointments with members | -1 | 2023-10-01 |  | Not Started | Low
4.04 | Evaluation | Thank You Emails | Email Chapter members who attended to say thank you for volunteering their time; Ask for evaluation forms and photos if they have not submitted; Ask them to send thank you emails to those they met with; Tip - schedule these to go out ahead of time | -1 | 2023-10-01 |  | Not Started | Low
4.05 | Evaluation | Thank You Emails | Send thank you emails to any partnering vendors such as your state medical society, catering, hotel, meeting venue, and transportation vendors; Tip - these can be scheduled ahead of time | -1 | 2023-10-01 |  | Not Started | Low
4.06 | Evaluation | Advertising the Day | Write a summary of the advocacy day and send to ACS State Affairs staff to publish in the Advocacy Brief | -5 | 2023-10-05 |  | Not Started | Low
4.07 | Evaluation | Advertising the Day | Publish summary of the advocacy day with photos in the Chapter newsletter (if available) | -5 | 2023-10-05 |  | Not Started | Low
4.08 | Evaluation | Evaluation Forms | Compile evaluation form comments to use as feedback for the next state advocacy day | -5 | 2023-10-05 |  | Not Started | Low
4.09 | Evaluation | Evaluation Forms | Share evaluation form comments and feedback with Chapter leadership | -10 | 2023-10-10 |  | Not Started | Low
4.1 | Evaluation | Follow-up Items | Schedule a follow-up presentation with ACS State Affairs staff to provide an update on how the day went and to call members to action | -10 | 2023-10-10 |  | Not Started | Low
4.11 | Evaluation | Follow-up Items | Submit State Advocacy Grant report to ACS State Affairs staff (if needed) | -10 | 2023-10-10 |  | Not Started | Low
Formulas:
Due Date = IF(ISBLANK(C2),,C2-[Days Until Advocacy Day])

## Legislative Appointments
Chamber | Legislator First and Last Name | District | Reasoning | Legislator Phone Number | Legislator Email | Office Location | Legislative Staff Contact | Legislative Staff Title | Legislative Staff Phone Number | Legislative Staff Email | Appointment Request Completed | Date Appointment Requested | Response | Appointment Time | Assigned Advocates | Notes
Assembly | Joe Schmoe | 86 | Sits on Health & Insurance Committee | (555) 555-1234 | jschmoe@texarkana.asm.gov | Capitol Building; Suite 100 | Sally Ann | Scheduler | (543) 216-7890 | sann@texarkana.asm.gov | Yes | 2024-02-05 | Yes | 14:30 | Calvin Harris, MD, FACS; Haley Jones, MD, FACS; Quill Manaheim, MD, FACS | Asm. Schmoe is a family physician.

## Do Not Delete (hidden)
DO NOT DELETE THIS PAGE. DO NOT ADJUST ANY FORMULAS.
Phases | Category | Status | Risk Level | Appointment Request Completed | Response
Conception | Advertising the Day | Not Started | Low | Yes | Yes
Production | Budget | In Progress | Medium | No | No
Launch | Building a Briefing Packet | On Hold | High |  | No Response
Evaluation | Catering | Complete | `
Choosing a Format
Choosing a Meeting Venue
Establishing Goals
Follow-up Items
Hotel Accomodations
Other
Meeting Materials
Recruiting Participants
Scheduling Legislative Appointments
Selecting a Date
Transportation
Meeting Presentations
Thank You Emails
Evaluation Forms
Chamber
Senate
House
Assembly